## Project Data
Project Name | RTDIP Timeseries Forecasting
Online team meeting | https://fau.zoom-x.de/j/65502405196?pwd=8H73lyixQfqKrnO8Eb47kawnuKCnGp.1
Production system (if any)
Test system (if any)
GitHub repository | https://github.com/amosproj/amos2025ws03-rtdip-timeseries-forecasting
GitHub feature board | https://github.com/orgs/amosproj/projects/91/
GitHub imp-squared backlog | https://github.com/orgs/amosproj/projects/96
Team T-shirt (white) | https://www.shirtinator.de/s/QWcDXTKGS72ISnrRNZq1hg
Team T-shirt (black) | https://www.shirtinator.de/s/0yx3duRjSzW-5hP32KmZ1w
Additional materials | https://discord.gg/KJXGmjcs
Team maling list | oss-amos-projX@lists.fau.de
Happines Index App | https://happy-amos.appspot.com/Courses

## Project Team
Last Name | First Name | GitHub User Name | Email Address
Böhm | Luca | qw3rat | luca.boehm@fau.de
Meusling | Patrick | SirGankalot | meusling@campus.tu-berlin.de
Arifin | Hafidz | zenzeii | h.arifin@campus.tu-berlin.de
Huy | Christoph | Perimora | christoph.huy@campus.tu-berlin.de
Selbig | Simon | simonselbig | simon.selbig@gmx.de
Haseeb | Abdul | abdulhaseeb-se | abdul.ah.haseeb@fau.de
Pohnke | Hannes | hpfref | hannes.j.pohnke@gmail.com
Jokiel | Rene | BelmontR | rene.jokiel@fau.de
Khabouze | Mehdi | Mehdi-kbz | khabouze@campus.tu-berlin.de

## Role Assignments
Product Owner
# | Meeting Day | Review | Planning | Software Developer | Release Manager | Scrum Master | Comment
1 | 2025-10-15 | Patrick Meusling | Hafidz Arifin | Everyone else | N/A | Luca
2 | 2025-10-22 | Hafidz Arifin | Patrick Meusling | Everyone else | Christoph | Luca
3 | 2025-10-29 | Patrick Meusling | Hafidz Arifin | Everyone else | Mehdi Khabouze | Luca
4 | 2025-11-05 | Hafidz Arifin | Patrick Meusling | Everyone else | Rene Jokiel | Luca
5 | 2025-11-12 | Patrick Meusling | Hafidz Arifin | Everyone else | Abdul Haseeb | Luca
6 | 2025-11-19 | Hafidz Arifin | Patrick Meusling | Everyone else | Hannes Pohnke | Luca
7 | 2025-11-26 | Patrick Meusling | Hafidz Arifin | Everyone else | Simon Selbig | Luca | Mid-term due
8 | 2025-12-03 | Hafidz Arifin | Patrick Meusling | Everyone else | Rene Jokiel | Luca
9 | 2025-12-10 | Patrick Meusling | Hafidz Arifin | Everyone else | Mehdi Khabouze | Luca
10 | 2026-01-11 | Hafidz Arifin | Patrick Meusling | Everyone else | Abdul Haseeb | Luca
11 | 2026-01-18 | Patrick Meusling | Hafidz Arifin | Everyone else | Hannes Pohnke | Luca
12 | 2026-01-25 | Hafidz Arifin | Patrick Meusling | Everyone else | Simon Selbig | Luca
13 | 2026-02-01 | Patrick Meusling | Hafidz Arifin | Everyone else | Mehdi Khabouze | Luca
14 | 2026-02-08 | Hafidz Arifin | Patrick Meusling | Everyone else | Christoph | Luca | Demo day!
15 | 2026-02-15 | Patrick Meusling | Hafidz Arifin | Everyone else | Hannes Pohnke | Luca | Retrospective
Product owners, software developers, and Scurm Master are set and ideally don't change over time; the critical part is the Release Manager role you need to define here
Formulas:
Meeting Day = [Meeting Day, row above]+7

## Team Contract
Goals | Aquire new skills
Produce a functioning and valuable product (a 1.0)
Meeting norms | We respect the opinions of others and we show up on time
Summary of Partner Meeting required
Working norms | Clean, testable code with clear commit messages, code comments
We respect other people's work
Coordination norms | Seperate branches for issues, second person review
We balance workload among the team
Communication norms | Daily check the corresponding channels (discord)
We communicate constructively, make sure to communicate possible problems (absence, etc.)
Consideration norms | We discuss issues openly
We vote in case we can't reach a consensus
Cont. improvement norms | We encourage critique and improvement efforts
Encourage reaching out for help (use the strength/skills of others)
Rewards | We treat ourselfes to a sweet of choice for good work
Sanctions | Push Ups (amount decided on the case)
Signatures
Scrum Master | Luca Böhm
Product owner | Patrick Meusling
Product owner | Hafidz Arifin
Software developer | Abdul Haseeb
Software developer | Rene Jokiel
Software developer | Simon Selbig
Software developer | Hannes Pohnke
Software developer | Christoph Huy
Software developer | Mehdi Khabouze

## Product Goal
Product Vision | Project Mission
The reason of existence of the envisioned product (beyond this project). | The mission of this particular project (in the context of the product vision).

## Product Glossary
Term | Definition

## Sprint Goals
Sprint # | Sprint goal
1 | None
2 | None
3 | None
4 | Optional
5 | Write your sprint goal here
6
7
8
9
10
11
12
13
14
15

## Velocity Tracking
Sprint # | Story Points Realized
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
PLEASE CREATE THE VELOCITY CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Mid-Project Release plan
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total |  |  | 0 | 0
Sprints
|  |  |  | Estimated burn-down |  | Real burn-down
1 |  |  | 0 | 0 | 0 | 0
2 |  |  | 0 | 0 | 0 | 0
3 |  |  | 0 | 0 | 0 | 0
... |  |  |  | 0 |  | 0
Features
1
2
3
PLEASE CREATE THE BURNDOWN CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Final Project Release plan
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total |  |  | 0 | 0
Sprints
|  |  |  | Estimated burn-down |  | Real burn-down
1 |  |  | 0 | 0 | 0 | 0
2 |  |  | 0 | 0 | 0 | 0
3 |  |  | 0 | 0 | 0 | 0
... |  |  |  | 0 |  | 0
Features
1
2
3
PLEASE CREATE THE BURNDOWN CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Definition of Done
# | Feature Definition of Done | Sprint Release Definition of Done | Project Release Definition of Done

## Documentation
Type | Link / reference

## Bill of Materials
Project: | RTIP - Forecasting and Anomaly Detection | System Components |  |  |  | First Level Dependencies and Runtimes | [5 empty] | Tools
Version | 0.1.0 (Sprint02)
Date | 28.10.2025
Last updated | 29.10.2025 | Name | Category | Source | Description | Name | Category | Version | License | Vendor | Description | Name | Category | Version | Description
Environment | Development | Forecasting | ML Component | src/sdk/python/rtdip_sdk/pipelines/forecasting | Train / Prediction with Forecasting Models. | Python | Runtime | 3.9 < 3.12.11 | PSF | Python Software Foundation | Core runtime for all SDK and ML components. | git | Development / Publish | 2.43.0 | Distributed version control system used for source code management and collaborative development.
Authors | Christoph Huy | Transformer | ML Pre-Processing | src/sdk/python/rtdip_sdk/pipelines/transformers/spark/machine_learning | Data / Feature pre-processing for ML components. | OpenJDK | Runtime | 11.0.27 | GPL v2 + Classpath Exception | OpenJDK Community | Java Virtual Machine required for Apache Spark and Delta Lake. | VS Code | Development | 1.105.1 | Integrated development environment used for coding, debugging, documentation editing, and Git integration.
|  | Data Manipulator | Data Quality | src/sdk/python/rtdip_sdk/pipelines/data_quality/data_manipulation | Alters data to ensure data quality. | Apache Spark (PySpark) | Runtime | 3.5.5 | Apache-2.0 | Apache Software Foundation | Distributed compute engine for ETL, data quality and forecasting pipelines. | Conda | Development / Build | 25.5.1 | Environment and package management system ensuring reproducible builds and dependency control.
|  | Monitor | Data Quality | src/sdk/python/rtdip_sdk/pipelines/data_quality/monitoring | Monitors quality of time-series data. | Delta Lake (delta-spark) | Runtime | 3.0.0 | Apache-2.0 | Linux Foundation / Databricks Open Source | Transactional storage layer enabling ACID and time-travel on Parquet data.
|  | Source | Data Extraction | src/sdk/python/rtdip_sdk/pipelines/sources | Ingest data source. | pandas | Library | 2.3.3 | BSD-3-Clause | PyData / NumFOCUS | Core data-processing library providing DataFrame operations and ETL utilities.
|  | Delta Storage | Data Storage | external (delta-spark) | Provides raw time-series data for ingestion and processing. | polars | Library | 0.20.31 | MIT | Polars Contributors | Fast DataFrame engine written in Rust for high-performance data manipulation.
[6 empty] | pyarrow | Library | 15.0.2 | Apache-2.0 | Apache Software Foundation | Columnar data access and Parquet I/O layer for Spark and Delta components.
[6 empty] | scikit-learn | Library | 1.7.2 | BSD-3-Clause | Scikit-learn Developers / NumFOCUS | Machine-learning algorithms and preprocessing utilities for forecasting and modeling.
|  | Upcomming |  |  |  | statsmodels | Library | 0.14.5 | BSD-3-Clause | Statsmodels Developers | Statistical modeling and time-series forecasting framework (e.g., SARIMA).
|  | Anomaly Detection | ML Component | TBA | Detects anomalies in time-series predictions. | pmdarima | Library | 2.0.4 | MIT | Alkha Management Group | Automated ARIMA model selection and time-series forecasting.
[6 empty] | delta-spark | Library | 3.0.0 | Apache-2.0 | Linux Foundation / Databricks | Delta Lake Python API for ACID table management and versioned data.
|  | ML Artifacts |  |  |  | databricks-sql-connector | Library | 3.7.1 | Apache-2.0 | Databricks Inc. | JDBC-style SQL connector for querying Delta and Databricks tables.
[6 empty] | fastapi | Library | 0.119.0 | MIT | Sebastián Ramírez | High-performance web framework for building REST APIs and model endpoints.
|  | Name | Category | Source | Description | uvicorn | Library | 0.37.0 | BSD-3-Clause | Encode OSS | ASGI server providing runtime execution for FastAPI endpoints.
|  | TBA |  |  |  | azure-core / azure-identity / azure-storage-blob | Library | 1.35 + | MIT | Microsoft Azure SDK | Core, authentication and blob-storage SDKs for Azure integration.
[6 empty] | pytest / pytest-cov | Library | 7.4 / 4.1 | MIT | Pytest Community | Unit and integration testing framework with coverage support.
[6 empty] | black / isort / pylint | Library | 25.1 / 5.13 / 2.17 | MIT / BSD-3 | Python Software Foundation / PyCQA | Code formatting and linting for CI quality assurance.
[6 empty] | mkdocs / mkdocs-material / mkdocstrings | Library | 1.6 / 9.5 / 0.25 | MIT | MkDocs Community | Documentation generation system for SDK and forecasting components.

## Planning Poker
Last Name | First Name | Value
Böhm | Luca |  | #DIV/0! | #DIV/0!
Meusling | Patrick
Arifin | Hafidz
Huy | Christoph
Selbig | Simon |  | 0 | No size
Haseeb | Abdul |  | 1 | Trivial size
Pohnke | Hannes |  | 2 | Small size
Jokiel | Rene |  | 3 | Medium size
Khabouze | Mehdi |  | 5 | Large size
|  |  | 8 | Very large size
|  |  | 13 | Too large (size)
How to play planning poker
1. Everyone type their number into their value field, don't hit return yet
2. Someone, perhaps a product owner, count down 3.. 2.. 1..
3. Then, everyone hit return to submit their value