## Project Data
Project Name | RTDIP Timeseries Forecasting
Online team meeting | https://fau.zoom-x.de/j/65502405196?pwd=8H73lyixQfqKrnO8Eb47kawnuKCnGp.1
Production system (if any)
Test system (if any)
GitHub repository | https://github.com/amosproj/amos2025ws03-rtdip-timeseries-forecasting
GitHub feature board | https://github.com/orgs/amosproj/projects/91/
GitHub imp-squared backlog | https://github.com/orgs/amosproj/projects/96
Team T-shirt (white) | https://www.shirtinator.de/s/QWcDXTKGS72ISnrRNZq1hg
Team T-shirt (black) | https://www.shirtinator.de/s/0yx3duRjSzW-5hP32KmZ1w
Additional materials | https://discord.gg/KJXGmjcs
Team maling list | oss-amos-projX@lists.fau.de
Happines Index App | https://happy-amos.appspot.com/Courses

## Project Team
Last Name | First Name | GitHub User Name | Email Address
Böhm | Luca | qw3rat | luca.boehm@fau.de
Meusling | Patrick | SirGankalot | meusling@campus.tu-berlin.de
Arifin | Hafidz | zenzeii | h.arifin@campus.tu-berlin.de
Huy | Christoph | Perimora | christoph.huy@campus.tu-berlin.de
Selbig | Simon | simonselbig | simon.selbig@gmx.de
Haseeb | Abdul | abdulhaseeb-se | abdul.ah.haseeb@fau.de
Pohnke | Hannes | hpfref | hannes.j.pohnke@gmail.com
Jokiel | Rene | BelmontR | rene.jokiel@fau.de
Khabouze | Mehdi | Mehdi-kbz | khabouze@campus.tu-berlin.de

## Role Assignments
Product Owner
# | Meeting Day | Review | Planning | Software Developer | Release Manager | Scrum Master | Comment
1 | 2025-10-15 | Patrick Meusling | Hafidz Arifin | Everyone else | N/A | Luca
2 | 2025-10-22 | Hafidz Arifin | Patrick Meusling | Everyone else | Christoph | Luca
3 | 2025-10-29 | Patrick Meusling | Hafidz Arifin | Everyone else | Mehdi Khabouze | Luca
4 | 2025-11-05 | Hafidz Arifin | Patrick Meusling | Everyone else | Rene Jokiel | Luca
5 | 2025-11-12 | Patrick Meusling | Hafidz Arifin | Everyone else | Abdul Haseeb | Luca
6 | 2025-11-19 | Hafidz Arifin | Patrick Meusling | Everyone else | Hannes Pohnke | Luca
7 | 2025-11-26 | Patrick Meusling | Hafidz Arifin | Everyone else | Simon Selbig | Luca | Mid-term due
8 | 2025-12-03 | Hafidz Arifin | Patrick Meusling | Everyone else | Rene Jokiel | Luca
9 | 2025-12-10 | Patrick Meusling | Hafidz Arifin | Everyone else | Mehdi Khabouze | Luca
10 | 2026-01-11 | Hafidz Arifin | Patrick Meusling | Everyone else | Abdul Haseeb | Luca
11 | 2026-01-18 | Patrick Meusling | Hafidz Arifin | Everyone else | Hannes Pohnke | Luca
12 | 2026-01-25 | Hafidz Arifin | Patrick Meusling | Everyone else | Simon Selbig | Luca
13 | 2026-02-01 | Patrick Meusling | Hafidz Arifin | Everyone else | Mehdi Khabouze | Luca
14 | 2026-02-08 | Hafidz Arifin | Patrick Meusling | Everyone else | Christoph | Luca | Demo day!
15 | 2026-02-15 | Patrick Meusling | Hafidz Arifin | Everyone else | Hannes Pohnke | Luca | Retrospective
Product owners, software developers, and Scurm Master are set and ideally don't change over time; the critical part is the Release Manager role you need to define here
Formulas:
Meeting Day = [Meeting Day, row above]+7

## Team Contract
Goals | Aquire new skills
Produce a functioning and valuable product (a 1.0)
Meeting norms | We respect the opinions of others and we show up on time
Summary of Partner Meeting required
Working norms | Clean, testable code with clear commit messages, code comments
We respect other people's work
Coordination norms | Seperate branches for issues, second person review
We balance workload among the team
Communication norms | Daily check the corresponding channels (discord)
We communicate constructively, make sure to communicate possible problems (absence, etc.)
Consideration norms | We discuss issues openly
We vote in case we can't reach a consensus
Cont. improvement norms | We encourage critique and improvement efforts
Encourage reaching out for help (use the strength/skills of others)
Rewards | We treat ourselfes to a sweet of choice for good work
Sanctions | Push Ups (amount decided on the case)
Signatures
Scrum Master | Luca Böhm
Product owner | Patrick Meusling
Product owner | Hafidz Arifin
Software developer | Abdul Haseeb
Software developer | Rene Jokiel
Software developer | Simon Selbig
Software developer | Hannes Pohnke
Software developer | Christoph Huy
Software developer | Mehdi Khabouze

## Product Goal
Product Vision | Project Mission
To empower organizations with open-source, scalable, and transparent forecasting capabilities that enable data-driven decision-making across industries. By extending RTDIP with advanced forecasting and anomaly detection components as well as sector specific datasets, we envision a future where time series insights such as trends, seasonality, and predictive patterns are seamlessly integrated into real-time data pipelines. This will allow businesses to understand historical data, anticipate future behavior, optimize operations, and improve efficiency using accessible, community-driven, and production-ready forecasting tools. | To design, develop, and contribute open-source forecasting components for the RTDIP platform that enable trend analysis, anomaly detection, and predictive modeling on time series data. Our mission within this project is to research and implement forecasting techniques using Python and Apache Spark, validate and enricht them with real-world datasets, and ensure they meet RTDIP’s modular, tested, and well-documented standards. By doing so, we will enhance RTDIP’s functionality and provide the open-source community and industry users such as Shell with reliable, scalable forecasting capabilities that integrate seamlessly into existing data pipelines.

## Product Glossary
Term | Definition
RTDIP (Real-Time Data Ingestion Platform) | An open-source project under the Linux Foundation designed to simplify the ingestion, transformation, and storage of data from various sources using scalable cloud technologies.
Forecasting | The process of predicting future values or trends based on historical time series data.
Time Series Data | Data collected over time at regular intervals, often used to analyze patterns such as trends and seasonality.
Apache Spark | An open-source distributed computing system that provides fast data processing for large-scale datasets.
PySpark | The Python API for Apache Spark, allowing developers to write Spark applications using Python.
Delta Lake | A storage layer that brings reliability, consistency, and performance to data lakes by supporting ACID transactions and schema enforcement.
Anomaly Detection | The identification of unusual patterns or outliers in data that do not conform to expected behavior.
Predictive Modeling | A statistical or machine learning approach that uses historical data to predict future outcomes.
Time Series Decomposition | The process of breaking down a time series into its core components such as trend, seasonality, and residuals.
ETL (Extract, Transform, Load) | A data pipeline process that extracts data from sources, transforms it into a suitable format, and loads it into a storage system.
Open Source | Software that is freely available to use, modify, and distribute, typically developed collaboratively by a community.
Linux Foundation | A nonprofit organization that supports open-source software projects and fosters collaboration across industries.
EasyCLA (Easy Contributor License Agreement) | A system used by the Linux Foundation to manage contributor license agreements, ensuring legal compliance for open-source contributions.
Modular Architecture | A software design principle that divides a system into separate, interchangeable components that can be developed and maintained independently.
Unit Testing | The practice of testing individual units or components of software to ensure they work as intended.
Documentation | Written descriptions and guides that explain the design, usage, and functionality of a software system.
Data Pipeline | A set of processes that move, transform, and store data from one system to another in a structured and automated way.
Scalability | The ability of a system to handle increasing amounts of work or data by adding resources.
Contribution Guidelines | A set of rules and best practices that contributors must follow to ensure consistency and quality in open-source projects.

## Sprint Goals
Sprint # | Sprint goal
1 | None
2 | None
3 | None
4 | Optional
5 | Establish a working foundation for the forecasting pipeline
6 | Integrate the pipeline into the existing software
7 | Advance the pipeline
8 | Add more Datasets to the pipeline
9 | Testing and Analysing the new Datasets
10 | Adding new and diffrent models to the pipeline
11 | Testing and Analysing the new Models
12 | Smaller features for more/diffrent preprocessing etc.
13 | Finishing the product so its ready
14 | Merging the product with the partner, coordinating the merge (they said this might take a bit of time)
15 | Backup Week

## Planning Poker
Last Name | First Name | Value
Böhm | Luca |  | #DIV/0! | #DIV/0!
Meusling | Patrick
Arifin | Hafidz
Huy | Christoph
Selbig | Simon |  | 0 | No size
Haseeb | Abdul |  | 1 | Trivial size
Pohnke | Hannes |  | 2 | Small size
Jokiel | Rene |  | 3 | Medium size
Khabouze | Mehdi |  | 5 | Large size
|  |  | 8 | Very large size
|  |  | 13 | Too large (size)
How to play planning poker
1. Everyone type their number into their value field, don't hit return yet
2. Someone, perhaps a product owner, count down 3.. 2.. 1..
3. Then, everyone hit return to submit their value

## Velocity Tracking
Sprint # | Story Points Realized
1 | 0
2 | 9
3 | 10
4 | 10
5 | 0
6
7
8
9
10
11
12
13
14
15
PLEASE CREATE THE VELOCITY CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Mid-Project Release plan
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total |  |  | 49 | 49
Sprints
|  |  |  | Estimated burn-down |  | Real burn-down
1 | None |  | 0 | 49 | 0 | 49
2 | None |  | 11 | 38 | 9 | 49
3 | None |  | 9 | 29 | 10 | 40
4 | Optional |  | 14 | 15 | 10 | 30
5 | Establish a working foundation for the forecasting pipeline |  | 15 | 0 | 0 | 20
6 | Integrate the pipeline into the existing software |  | 0 | 0 | 0 | 20
Features
1 | None
2 | None
|  | Run the software on your own machine | 1 |  | 1
|  | Understanding the rtdip software | 2 |  | 2
|  | Software Architecture | 2 |  | 2
|  | Find open source time series datasets | 2 |  | 2
|  | Initialize software bill of materials | 2 |  | 2
|  | Research about time series forecasting fundamentals | 2 |  | NotCompleted
3 | None
|  | Research Possible Models Useful for Shell Dataset | 2 |  | 2
|  | Update our Forked Repository with Latest RTDIP Release | 1 |  | 1
|  | Prepare and Demo Project Build Process | 1 |  | 2
|  | Perform Data Exploration on Shell Dataset | 3 |  | 3
|  | Research about time series forecasting fundamentals | 2 |  | 2
4 | Optional
|  | Getting to Know HPC of AMOS | 2 |  | NotCompleted
|  | Perform Data Exploration on Opensource Dataset 1 | 2 |  | 3
|  | Preprocess Shell Dataset | 3 |  | 3
|  | Implementing a basic Model pipeline | 2 |  | 2
|  | Research Possible Models Userful fo Opensource Dataset | 2 |  | NotCompleted
|  | CI/CD Pipeline fail bug | 3 |  | 2
5 | Establish a working foundation for the forecasting pipeline
|  | Choosing Models, Datasets, Error Measure Metrics | 2
|  | Create Build Process Video | 2
|  | Model Training and Evaluation with Shell Dataset | 3
|  | Visualization of Results | 2
|  | Preprocess Opensource Dataset 1 | 3
|  | PO Homework | 3
6 | Integrate the pipeline into the existing software
Model Deployment Pipeline into RTDIP
User/Design/Build Documentation
Repository Structure Refactor
Update Software Architecture
Set Up Unified Development Environment
Collect and Document Customer Feedback on Project Progress
Model Optimization and Improvement
Model Training and Evaluation with Opensource Dataset 1
PLEASE CREATE THE BURNDOWN CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Final Project Release plan
Sprint | Goal | Feature Name | Est. size | Est. remaining | Real size | Real remaining
Release
Total |  |  | 0 | 0
Sprints
|  |  |  | Estimated burn-down |  | Real burn-down
1 |  |  | 0 | 0 | 0 | 0
2 |  |  | 0 | 0 | 0 | 0
3 |  |  | 0 | 0 | 0 | 0
... |  |  |  | 0 |  | 0
Features
1
2
3
PLEASE CREATE THE BURNDOWN CHART ON A NEW TAB USING THE DATA FROM THIS TAB

## Definition of Done
# | Feature Definition of Done | Sprint Release Definition of Done | Project Release Definition of Done
Acceptance criteria are met.
Work are pushed to the Github repository.
Create a branch for each backlog items (coding)
A pull request is created for each related branch.
The work products in the pull requests are reviewed.
The corresponding branches are merged and closed.
The bill of materials section of the planning documents is updated.
Work needs to be documented in the corresponding wiki section
For new features unit test have to be written.
Update our forked repository with the latest RTDIP release.
If the task involves coding, the implementation is integrated into the RTDIP framework and verified to function correctly within it.
Release candidates with a working and meaningful update to the previous sprint is tagged.
Previously established features must continue to work.
The RTDIP forecasting components can be successfully built and deployed within the RTDIP environment.
All automated tests and validation checks for the developed components pass without errors.
The implemented forecasting features have been tested end-to-end and verified through a basic user workflow.
Developer documentation is complete, clearly describing the architecture, setup, and contribution process for RTDIP.
User documentation (usage examples, configuration steps, expected outputs) is finalized and up to date.
The final release has been reviewed and approved by all project team members and the industry partner (Shell).

## Documentation
Type | Link / reference

## Bill of Materials
Project: | RTIP - Forecasting and Anomaly Detection | System Components |  |  |  | First Level Dependencies and Runtimes | [5 empty] | Tools
Version | 0.1.0 (Sprint02)
Date | 28.10.2025
Last updated | 29.10.2025 | Name | Category | Source | Description | Name | Category | Version | License | Vendor | Description | Name | Category | Version | Description
Environment | Development | Forecasting | ML Component | src/sdk/python/rtdip_sdk/pipelines/forecasting | Train / Prediction with Forecasting Models. | Python | Runtime | 3.9 < 3.12.11 | PSF | Python Software Foundation | Core runtime for all SDK and ML components. | git | Development / Publish | 2.43.0 | Distributed version control system used for source code management and collaborative development.
Authors | Christoph Huy | Transformer | ML Pre-Processing | src/sdk/python/rtdip_sdk/pipelines/transformers/spark/machine_learning | Data / Feature pre-processing for ML components. | OpenJDK | Runtime | 11.0.27 | GPL v2 + Classpath Exception | OpenJDK Community | Java Virtual Machine required for Apache Spark and Delta Lake. | VS Code | Development | 1.105.1 | Integrated development environment used for coding, debugging, documentation editing, and Git integration.
|  | Data Manipulator | Data Quality | src/sdk/python/rtdip_sdk/pipelines/data_quality/data_manipulation | Alters data to ensure data quality. | Apache Spark (PySpark) | Runtime | 3.5.5 | Apache-2.0 | Apache Software Foundation | Distributed compute engine for ETL, data quality and forecasting pipelines. | Conda | Development / Build | 25.5.1 | Environment and package management system ensuring reproducible builds and dependency control.
|  | Monitor | Data Quality | src/sdk/python/rtdip_sdk/pipelines/data_quality/monitoring | Monitors quality of time-series data. | Delta Lake (delta-spark) | Runtime | 3.0.0 | Apache-2.0 | Linux Foundation / Databricks Open Source | Transactional storage layer enabling ACID and time-travel on Parquet data.
|  | Source | Data Extraction | src/sdk/python/rtdip_sdk/pipelines/sources | Ingest data source. | pandas | Library | 2.3.3 | BSD-3-Clause | PyData / NumFOCUS | Core data-processing library providing DataFrame operations and ETL utilities.
|  | Delta Storage | Data Storage | external (delta-spark) | Provides raw time-series data for ingestion and processing. | polars | Library | 0.20.31 | MIT | Polars Contributors | Fast DataFrame engine written in Rust for high-performance data manipulation.
[6 empty] | pyarrow | Library | 15.0.2 | Apache-2.0 | Apache Software Foundation | Columnar data access and Parquet I/O layer for Spark and Delta components.
[6 empty] | scikit-learn | Library | 1.7.2 | BSD-3-Clause | Scikit-learn Developers / NumFOCUS | Machine-learning algorithms and preprocessing utilities for forecasting and modeling.
|  | Upcomming |  |  |  | statsmodels | Library | 0.14.5 | BSD-3-Clause | Statsmodels Developers | Statistical modeling and time-series forecasting framework (e.g., SARIMA).
|  | Anomaly Detection | ML Component | TBA | Detects anomalies in time-series predictions. | pmdarima | Library | 2.0.4 | MIT | Alkha Management Group | Automated ARIMA model selection and time-series forecasting.
[6 empty] | delta-spark | Library | 3.0.0 | Apache-2.0 | Linux Foundation / Databricks | Delta Lake Python API for ACID table management and versioned data.
|  | ML Artifacts |  |  |  | databricks-sql-connector | Library | 3.7.1 | Apache-2.0 | Databricks Inc. | JDBC-style SQL connector for querying Delta and Databricks tables.
[6 empty] | fastapi | Library | 0.119.0 | MIT | Sebastián Ramírez | High-performance web framework for building REST APIs and model endpoints.
|  | Name | Category | Source | Description | uvicorn | Library | 0.37.0 | BSD-3-Clause | Encode OSS | ASGI server providing runtime execution for FastAPI endpoints.
|  | TBA |  |  |  | azure-core / azure-identity / azure-storage-blob | Library | 1.35 + | MIT | Microsoft Azure SDK | Core, authentication and blob-storage SDKs for Azure integration.
[6 empty] | pytest / pytest-cov | Library | 7.4 / 4.1 | MIT | Pytest Community | Unit and integration testing framework with coverage support.
[6 empty] | black / isort / pylint | Library | 25.1 / 5.13 / 2.17 | MIT / BSD-3 | Python Software Foundation / PyCQA | Code formatting and linting for CI quality assurance.
[6 empty] | mkdocs / mkdocs-material / mkdocstrings | Library | 1.6 / 9.5 / 0.25 | MIT | MkDocs Community | Documentation generation system for SDK and forecasting components.